## Project Overview
Item | Description
Project Name | Relay & Dimmer Control Mobile Application
Project Description | A cross-platform Android/iOS application for monitoring and controlling automation relays, DC/AC lighting dimming modules, blind motor control, and temperature modules over local LAN (TCP/IP) and remote MQTT with automatic fallback, including cloud backup, scenarios, smart automations, and event logging.
Target Platforms | Android, iOS (cross-platform, single codebase)
Primary Users | Home owners, building automation integrators, electricians, facility administrators
Key Objectives | 1. Provide direct local control of relay and dimming outputs with low latency via TCP/IP; 2. Enable reliable remote control via MQTT with automatic LAN fallback; 3. Support scenario (tap-to-run) and smart automation (time/device-state based) programming; 4. Deliver cloud-based account, backup, restore and multi-device sync; 5. Provide monitoring via event log, temperature alerts, and push notifications.
Scope (in-scope items) | Single-location architecture (designed for future multi-location); Account management (registration, auth, password recovery); Cloud backup/restore and multi-device sync; Module discovery via self-discovery and by IP; Local and remote control with LAN/MQTT fallback; Output/channel management (naming, icons, ON/OFF); Physical input modes (momentary, toggle, associated); Dedicated control UIs for relay, DC blind, DC dimmer, AC dimmer, and temperature modules; Scenarios with multiple actions and manual dimmer sliders; Smart automations (time and device-state based); Event log with 30-day retention; Rooms/zones and scenario assignment; Home screen quick buttons with drag-and-drop; Offline alerts and System Status page; Push notifications; Localization in Romanian and English at launch.
Out of Scope (explicitly from brief) | Advanced thermostat functionality (deferred to a future level); Cloud portal for remote equipment administration (deferred); Multi-location live support (architecture ready but single-location initially); Localization beyond Romanian and English at launch.
Assumptions | Stable Wi-Fi/LAN availability is normal for local control; MQTT broker and cloud backend services are available and provisioned; Modules support documented TCP/IP/API and MQTT protocols; Push notification services (FCM/APNs) are configured; App Store / Play Store submission follows standard review process.
Constraints | Requires an active account and internet connection for cloud sync and remote control; Local control requires the device on the same LAN as modules; MQTT remote control depends on broker connectivity; Native push notification behavior varies by OS (APNs/FCM); Single-location restriction until multi-location phase.

## Functional Requirements
Requirement ID | Feature Area | Description | Priority (High/Medium/Low) | Acceptance Criteria | Dependencies
FR-001 | Account Management | User can create an account using email and password. | High | User can register with a valid email and password and is logged in automatically on success. Duplicate emails are rejected. | Cloud backend (Firebase Auth)
FR-002 | Account Management | User can authenticate with email and password. | High | Registered user can log in with correct credentials and is denied access with an error for incorrect credentials. | FR-001
FR-003 | Account Management | User can recover a lost password via email. | High | User can request a password reset link via email and reset the password; confirmation email is sent. | Cloud email service
FR-004 | Account Management | User can log out securely. | High | Logged-out user cannot access protected data; local sensitive data cleared. | FR-002
FR-005 | Cloud Backup | Automatic cloud backup of configurations. | High | All modules, channels, scenarios and settings are automatically backed up to the cloud on change. | Cloud DB
FR-006 | Cloud Restore | Restore backup on a new device. | High | User can restore configuration to a new device from cloud; restored data matches last backup. | FR-005
FR-007 | Multi-device Sync | Synchronize configuration across devices of same account. | High | Changes on one device propagate to others logged into the same account. | FR-005
FR-008 | Module Management | Discover modules via self-discovery message. | High | Modules broadcasting self-discovery appear in the device list automatically. | LAN TCP/IP support
FR-009 | Module Management | Add module manually by IP address. | High | User can add a module manually by entering an IP address; module is validated as reachable. | FR-008
FR-010 | Module Management | Indicate online/offline status (green/red dot). | High | Each module shows green when reachable and red when unreachable within polling interval. | LAN/MQTT connectivity
FR-011 | Communication | Local control via TCP/IP or module APIs. | High | Commands sent locally over LAN are executed by modules within acceptable latency. | Module protocol
FR-012 | Communication | Remote control via MQTT. | High | Remote commands published over MQTT reach modules and execute correctly. | MQTT broker
FR-013 | Communication | Automatic LAN to MQTT fallback. | High | If LAN becomes unavailable, control automatically switches to MQTT without user intervention. | FR-011, FR-012
FR-014 | Channel Management | Direct ON/OFF control of outputs. | High | User can toggle an output ON/OFF instantly from the list or detail screen. | FR-011
FR-015 | Channel Management | Rename and assign icons to outputs. | Medium | User can name each output and associate an icon displayed in the UI. | Local DB
FR-016 | Input Configuration | Configure physical input modes: momentary, toggle, associated. | Medium | User can set each physical input to momentary, toggle or associated mode and behavior reflects accordingly. | Module protocol
FR-017 | Relay Module UI | Dedicated relay control interface. | High | Relay module screen shows each channel with ON/OFF control and status. | FR-014
FR-018 | Blind Module UI | Dedicated DC blind motor control with UP/DOWN toggle. | High | Blind screen provides UP/DOWN/STOP control with correct toggle logic. | Module protocol
FR-019 | Dimmer Module UI | Dedicated DC dimmer (12-24V) control. | High | Dimmer screen provides 0-100% brightness slider and preset. | Module protocol
FR-020 | Dimmer Module UI | Dedicated AC dimmer (220V) control. | High | AC dimmer screen provides 0-100% brightness slider and preset. | Module protocol
FR-021 | Temperature Module UI | Dedicated temperature module monitoring and thresholds. | High | Temperature screen shows current temperature and allows threshold configuration with alerts. | Module protocol
FR-022 | Scenario Management | Create tap-to-run scenarios. | High | User can create a scenario that executes when tapped. | Scenario editor
FR-023 | Scenario Management | Support multiple actions per scenario across modules. | High | A scenario can include several actions on different modules executed on run. | FR-022
FR-024 | Scenario Management | Set precise brightness levels in scenario actions. | High | Scenario actions can set a dimmer to a precise brightness percentage. | FR-019, FR-020
FR-025 | Scenario Management | Manual dimmer slider within scenario. | Medium | A scenario can include a manual dimmer slider action for interactive adjustment. | FR-024
FR-026 | Smart Automation | Time-based (time-of-day) automations. | Medium | User can configure IF (time of day) THEN (action) automations; executed when time matches. | Scenario engine
FR-027 | Smart Automation | Device-state-based automations. | Medium | User can configure IF (device state) THEN (action) automations; executed on state change. | Scenario engine
FR-028 | Event Log | Record events with 30-day retention. | High | Actions and system events are logged with timestamps and retained for 30 days; older entries purged. | Local/cloud DB
FR-029 | Rooms/Zones | Create rooms/zones and assign scenarios. | Medium | User can create rooms/zones and assign scenarios to them for organization. | FR-022
FR-030 | Home Screen | Quick scenario buttons on home screen. | High | Home screen shows quick action buttons that run scenarios on tap. | FR-022
FR-031 | Home Screen | Drag-and-drop ordering of scenario buttons. | Medium | User can reorder home scenario buttons via drag-and-drop; order is saved. | FR-030
FR-032 | Home Screen | Offline module alert banner. | High | A banner or the System Status page indicates offline modules. | FR-010
FR-033 | Home Screen | Temperature alert on home screen. | High | Home screen reflects temperature threshold alert when triggered. | FR-021
FR-034 | Push Notifications | Notify on module offline/online transition. | Medium | Push notification sent when a module goes offline or returns online. | FCM/APNs
FR-035 | Push Notifications | Notify on long-running output. | Medium | Notification alerts when an output has been running beyond configured duration. | FR-014
FR-036 | Push Notifications | Notify on temperature threshold breach. | High | Notification sent when measured temperature exceeds configured threshold. | FR-021
FR-037 | System Status | System Status page with error log. | Medium | A page lists module status and error log entries for troubleshooting. | FR-028
FR-038 | Multi-location | Multi-location architectural support (single-location initially). | Medium | Data model and services support multiple locations while the app currently creates/uses a single location. | Cloud data model
FR-039 | Localization | Romanian and English localization at launch. | High | All user-facing strings are localized in Romanian and English with a language selector. | i18n system

## Module Types & Channel Specific
Module Type | Number of Channels/Outputs | Control Type | Communication Protocol | Special Features | Notes
Standard Relay Module | Multiple (e.g., 2-8 relay channels) | Direct ON/OFF (electromechanical) | TCP/IP and MQTT | Per-channel naming and icons; online/offline status; long-running output detection | Used for general on/off loads such as lights, sockets and pumps; supports physical input association.
DC Blind Motor Control Module | One or more blind channels | UP/DOWN/STOP (motor toggle logic) | TCP/IP and MQTT | Directional toggle logic; stop command; travel/time-based positioning | Dedicated interface with UP/DOWN/STOP buttons and blind position handling.
DC Lighting Dimming Module (12-24V) | Multiple dimmable channels | 0-100% dimming | TCP/IP and MQTT | Continuous brightness slider; precise brightness presets; constant/STEP dimming levels | Supports configurable dimming levels; scenario brightness actions.
AC Lighting Dimming Module (220V) | Multiple dimmable channels | 0-100% dimming | TCP/IP and MQTT | Continuous brightness slider; precise brightness presets for 220V loads | Supports trailing/leading edge dimming loads; mains-rated isolation.
Temperature Module | One or more temperature sensors | Monitoring only (read + thresholds) | TCP/IP and MQTT | Temperature reading; configurable high/low threshold; alert generation | Feeds home temperature alerts and push notifications; advanced thermostat deferred.

## Data Model
Entity | Field | Data Type | Description | Relationships
User | id; email; passwordHash; displayName; createdAt | string; string; string; string; date | Account holder identity and credentials. | Has many Locations
User | language; notificationPreferences | string; map | Localization and notification settings. | References Notification Preference
Location | id; name; userId; isPrimary | string; string; string; boolean | Physical place (building/site) owning modules; single-location at launch. | Belongs to User; Has many Modules, Rooms/Zones
Module | id; locationId; type; name; ipAddress | string; string; enum; string; string | Physical device; relay/blind/dimmer/temperature. | Belongs to Location; Has many Channels/Outputs
Module | status; communicationPath; mqttTopic | enum; enum; string | Online/offline and TCP/MQTT path; MQTT addressing. | Read by System Status
Channel/Output | id; moduleId; number; name; type | string; string; int; string; enum | Addressable output on a module. | Belongs to Module
Channel/Output | state; brightness; icon; longRunningLimit | enum; int; string; int | Current state/value; display and safety properties. | Referenced by Scenario Actions
Input Configuration | id; moduleId; inputNumber; mode | string; string; int; enum | Physical input wiring mode: momentary, toggle, associated. | Belongs to Module
Scenario | id; locationId; name; icon; order | string; string; string; string; int | User-defined tap-to-run automation. | Belongs to Location; Has many Scenario Actions; Assignable to Rooms/Zones
Scenario Action | id; scenarioId; channelId; action; value | string; string; string; enum; value | Single instruction in a scenario (ON/OFF/brightness). | Belongs to Scenario; References Channel/Output
Room/Zone | id; locationId; name; icon | string; string; string; string | Logical grouping of scenarios/areas. | Belongs to Location; Assigns Scenarios
Event Log Entry | id; timestamp; moduleId; type; detail | string; date; string; enum; string | Recorded system/action event; 30-day retention. | References Module; Related to alerts
Temperature Alert | id; temperatureModuleId; threshold; direction; triggeredAt; clearedAt | string; string; enum; date; date | Threshold breach state for a temperature module. | Belongs to Temperature Module; Generates Notifications
Notification Preference | id; userId; events; channels | string; string; list; list | Which events notify and via which channels. | Belongs to User; Feeds Push Notification logic

## UIUX Specifications
Screen/Component | Key Elements | Behavior/Interaction | Design Notes (minimalist, high-contrast, large buttons)
Login/Register/Forgot Password | Email field, password field, submit, links to register and forgot password | Login validates credentials; forgot password sends reset email; register creates account. | Minimalist layout; high-contrast text/inputs; large tap targets.
Home (tab) | Quick scenario buttons, module summary, alert banners | Buttons run scenarios on tap; offline and temperature banners shown; drag-and-drop reorder. | Minimalist grid; high-contrast on/off colors; large scenario buttons.
System Status page | Module list with green/red dots, error log | Shows online/offline status and recent errors for troubleshooting. | Status dots high-contrast; clear hierarchy.
Configuration (tab) - Device List | Module list, add button, discovery status | Lists discovered modules; add-by-IP; shows online/offline. | Large add button; consistent status indicators.
Module Detail (relay) | Channel ON/OFF switches | Large toggles with per-channel status and names. | Large switches; high-contrast ON/OFF states.
Module Detail (blind) | UP, DOWN, STOP buttons | Buttons drive motor with toggle/stop logic; position indicator. | Large labeled control buttons.
Module Detail (dimmer) | Brightness slider, presets | Slider sets 0-100%; presets one-tap. | Wide, tall slider; large numerical readout.
Module Detail (temperature) | Temperature readout, threshold settings | Shows live temperature; threshold config triggers alert. | Large readout; clear threshold configuration.
Channel/Output Configuration | Name field, icon picker | Rename output and associate icon shown in UI. | Simple forms; accessible icon grid.
Physical Input Configuration | Mode selector (momentary/toggle/associated) | Set behavior of each physical input. | Clear segmented control.
Scenario List | Scenario names, tap-to-run, reorder | Listing with quick-run and drag-and-drop ordering. | Large tap-to-run buttons; reorder handles.
Scenario Editor | Action list builder, add/remove actions | Add actions across modules; set precise values incl. brightness. | Structured builder; undo support.
Automation Rules (IF/THEN) | Condition builder, action builder | Create time-based or device-state-based rules with THEN actions. | Clear IF/THEN visual structure.
Event History | Timeline with filters, retained 30 days | Logs actions/events with timestamp; filter by type/module. | Readable list with time and type.
Rooms Management | Room list, create/edit, scenario assignment | Create rooms/zones and assign scenarios for organization. | Simple cards and assignment UI.
Settings | Account, Notifications, Backup/Sync sections | Manage profile, notification preferences, and backup/sync state. | Grouped sections; clear toggles.
Offline Alert Banner | Warning banner with module name | Appears on home/status when modules offline; high-contrast attention color. | Prominent but non-blocking banner.
Temperature Alert Banner | Warning banner with sensor/threshold | Appears when threshold breached; high-contrast attention color. | Prominent but non-blocking banner.
Drag-and-drop reorder for home scenario buttons | Long-press handle, drop target | Long-press to lift and reorder buttons; order persisted. | Visible reorder affordance.
Manual dimmer slider | Large slider control | Draggable slider adjusts brightness smoothly within a scenario or module detail. | Wide, tall slider; real-time feedback.

## Technical Architecture
Component | Technology/Approach | Description | Integration Points
Cross-platform framework | Flutter (Dart) | Single codebase for Android/iOS UI with native compile. | Links to all UI feature modules
State management | Provider / Riverpod (or Bloc) | Centralized app state for modules, scenarios, settings and sync. | UI, repositories, services
Local storage | SharedPreferences / SQLite (sqflite) / Hive | Persist local config, offline cache and event-log buffer. | Repositories, sync service
TCP/IP communication | Raw TCP sockets or vendor HTTP/API client | Direct local commands to modules on LAN with low latency. | Module service, discovery
MQTT communication | MQTT client (mqtt.dart) + broker | Remote publish/subscribe for module control and status over internet. | Module service, fallback logic
Cloud backend | Firebase (Auth + Cloud Firestore + Cloud Functions) | User auth, configuration store, sync and restore logic. | Auth, Data Model, Fallback
Push notifications | FCM (Android) / APNs (iOS) | Deliver offline/online, long-running-output and temperature alerts. | Notification preferences, alerting
Localization system | intl + ARB/JSON resource files | Structured translation catalogs with runtime language switching (RO/EN). | UI, settings
CI/CD pipeline | Git-based CI (GitHub Actions) + CodeMagic/Fastlane | Automated build, test, analysis and store deployment for iOS/Android. | Repo, stores, test suites
LAN/MQTT fallback logic | Connectivity monitor + service locator | Detect LAN availability and switch control path automatically between TCP and MQTT. | Module service, status

## Localization Plan
Language | Status | Implementation Notes
Romanian (at launch) | Active | Full translation of all UI strings; verified by native reviewers; default for RO locale; part of MVP acceptance.
English (at launch) | Active | Primary/fallback language; source of truth for message keys; bundled and fully testable at launch.
Spanish (future) | Planned | Translation catalog created later; not implemented in MVP; to be added in a future release cycle.
French (future) | Planned | Translation catalog created later; not implemented in MVP; to be added in a future release cycle.
German (future) | Planned | Translation catalog created later; not implemented in MVP; to be added in a future release cycle.

## Security & Account Management
Area | Requirement | Implementation Approach
Email/password authentication | User registers and logs in with email and password. | Firebase Authentication email/password provider with secure credential hashing managed by backend.
Password reset via email | User can recover a lost password via email link. | Firebase built-in reset email flow; link opens secure reset page returning to app.
Secure cloud backup | Configuration automatically backed up to cloud. | Write operations persisted to Firestore; backups scoped to the authenticated user only.
Multi-device synchronization | Same-account devices stay in sync. | Cloud Functions/real-time listeners propagate changes; conflict resolution via last-write/versioning.
Data isolation per user | Users only see their own data. | Firestore security rules restrict reads/writes to the authenticated user's UID and owned resources.
Encryption in transit | All communication is secure. | TLS for cloud/MQTT and LAN where supported; credentials and tokens never stored in plain text.
Firestore/Firebase security rules | Unauthorized access is prevented. | Rule-set enforcing ownership checks on all collections; deny-by-default policy.
Session management | Sessions persist and revoke safely. | Token refresh management; logout clears local auth and sensitive cache; optional token revocation.

## Testing Strategy
Test ID | Test Category | Test Scenario | Expected Result | Priority | Hardware Required?
TC-001 | Acount | User registers, logs in, logs out | Registration succeeds, login works, logout clears session | High | No
TC-002 | Account | Password recovery via email | Reset email sent; password updated; login with new password | High | No
TC-003 | Cloud | Backup and restore on new device | New device restores full configuration from cloud | High | No
TC-004 | Cloud | Multi-device sync | Changes on one device appear on another for same account | High | No
TC-005 | Module | Module discovery and addition by IP | Discovered modules and IP-added modules appear in list | High | Yes
TC-006 | Module | Online/offline status detection | Green/red dot reflects reachability | High | Yes
TC-007 | Control | Direct relay ON/OFF | Relay toggles ON/OFF correctly over LAN | High | Yes
TC-008 | Control | Blind up/down toggle logic | UP/DOWN/STOP behaves correctly | High | Yes
TC-009 | Control | DC/AC dimmer slider (0-100%) | Slider sets brightness to expected percentage | High | Yes
TC-010 | Monitoring | Temperature monitoring and threshold alerts | Reading updates and threshold alert triggers | High | Yes
TC-011 | Input | Physical input modes (momentary, toggle, associated) | Each mode behaves as configured | Medium | Yes
TC-012 | Scenario | Scenario creation and execution | Tap-to-run executes all actions | High | Yes
TC-013 | Scenario | Manual dimmer slider scenario | Slider action adjusts brightness within scenario | Medium | Yes
TC-014 | Automation | Time-based trigger | Automation runs at configured time | Medium | Yes
TC-015 | Automation | Device-state trigger | Automation runs on device state change | Medium | Yes
TC-016 | Event | Event log recording and 30-day retention | Events logged; entries older than 30 days purged | High | Yes
TC-017 | Rooms | Room creation and scenario assignment | Rooms created and scenarios assigned/organized | Medium | No
TC-018 | Home | Drag-and-drop order of scenarios | Order reordered and persisted | Medium | No
TC-019 | Status | Offline banner and System Status page | Offline modules shown and errors listed | High | Yes
TC-020 | Notifications | Offline/online, long-running output, temperature alerts | Push notifications correctly delivered | Medium | Yes
TC-021 | Failover | LAN to MQTT failover | Control continues via MQTT when LAN unavailable | High | Yes

## Milestones & Deliverables
Stage | Description | Key Tasks | Deliverable | Estimated Timeline | Dependencies | Acceptance Criteria
Stage 1 | Project setup and architecture | Repository scaffold, CI/CD, framework selection, cloud provisioning, architectural design document | Working dev environment and CI; architecture doc | 2-3 weeks | None | Build pipeline runs; architecture approved
Stage 2 | Account and cloud foundation | Authentication, backup/restore, multi-device sync, data model implementation | Auth + cloud sync/restore functional | 3-4 weeks | Stage 1 | Register/login/reset/sync/restore pass tests
Stage 3 | Module discovery and communication | Self-discovery, add-by-IP, LAN TCP/MQTT, fallback logic, status indicators | Module connectivity and status layer | 4-5 weeks | Stage 2 | Discovery, status, LAN/MQTT fallback pass tests
Stage 4 | Core control interfaces | Relay, blind, dimmer (DC/AC), temperature UIs and channel/input configuration | Control screens functional | 4-5 weeks | Stage 3 | Direct control and monitoring pass hardware tests
Stage 5 | Scenarios and automations | Scenario editor, tap-to-run, dimmer slider, time and device-state automations, rooms | Automation features functional | 4-5 weeks | Stage 4 | Scenario and automation tests pass
Stage 6 | Notifications, events, localization, polish | Push notifications, event log/30-day retention, System Status, RO/EN localization, home screen drag-and-drop | Full-feature app with localization | 3-4 weeks | Stage 5 | Notification, log retention, localization accepted
Stage 7 | Testing, release, store submission | Hardware/matrix testing, UAT, app store submission, store review and launch | Release version submitted and approved | 3-4 weeks | Stage 6 | Store approval; MVP acceptance criteria met

## Risks & Mitigations
Risk ID | Risk Description | Likelihood (High/Medium/Low) | Impact (High/Medium/Low) | Mitigation Strategy
RSK-001 | Hardware delivery delays | Medium | High | Order hardware early, maintain test fixtures, define contingency with local bench/module suppliers.
RSK-002 | Incomplete or unclear vendor API documentation | High | High | Request and validate protocol docs early; clarify with vendor; build protocol adapters with fallback parsing.
RSK-003 | LAN and MQTT fallback instability | Medium | High | Robust connectivity monitoring, logging handoffs, extensive failover test matrix.
RSK-004 | Dimmer module compatibility issues | Medium | High | Prototype with real dimmers early, maintain supported-load matrix (LED/incandescent/mains).
RSK-005 | Cloud sync conflicts | Medium | Medium | Versioning and last-write-wins plus field-level merge; expose sync state; add conflict tests.
RSK-006 | Push notification delivery failures | Medium | Medium | Use FCM/APNs best practices, device-token refresh, fallback to in-app banners and System Status.
RSK-007 | App Store review delays | Low | High | Prepare privacy/metadata early, follow store guidelines, build in review buffer in schedule.
RSK-008 | Localization scope creep | Medium | Low | Lock RO/EN at launch (MVP), defer other languages, define translation scope in contract.

## User Management Specification
Requirement ID | Feature | Description | Priority | Notes
UM-001 | Registration | Create an account with email and password. | High | Required for MVP; auto-login on success.
UM-002 | Login | Authenticate with existing credentials. | High | Required for access to user data.
UM-003 | Logout | Securely end the session. | High | Clears local sensitive data and token.
UM-004 | Password recovery | Reset a lost password via email link. | High | Email-based reset flow using provider.
UM-005 | Cloud backup | Automatically back up configuration to cloud. | High | Persisted on change; user-scoped.
UM-006 | Restore | Restore configuration on a new device. | High | Full restore to match last valid backup.
UM-007 | Multi-device sync | Synchronize same-account devices. | High | Real-time propagation of changes.
UM-008 | Single-location initial support | One location per user at launch. | Medium | MVP limited to a single primary location.
UM-009 | Multi-location readiness | Architecture supports future multiple locations. | Medium | Data model services location-aware but not exposed at launch.

## MVP Scope
Feature Area | Feature Description | MVP Must-Have (Yes/No) | Priority (High/Medium/Low) | Rationale | Dependencies
Account | Mandatory account creation and email/password authentication | Yes | High | Essential for data isolation, backup and sync. | Auth backend
Account | Password recovery via email | Yes | High | Required account usability. | Email service
Cloud | Automatic cloud backup and restore | Yes | High | Prevents data loss on device change. | Cloud backend
Sync | Multi-device synchronization via account | Yes | High | Core user value. | Cloud backend
Module | Module discovery via self-discovery message | Yes | High | Simplifies setup. | LAN protocol
Module | Module identification by IP address | Yes | High | Manual fallback for discovery. | LAN protocol
Module | Online/offline status indicator (green/red dot) | Yes | High | Core monitoring need. | Connectivity
Control | Local LAN control via TCP/IP or APIs | Yes | High | Low-latency local control. | Module protocol
Control | Remote control via MQTT | Yes | High | Access outside LAN. | Broker
Control | Automatic LAN to MQTT fallback | Yes | High | Resilience of control. | TCP+MQTT
Channel | Output/channel direct ON/OFF control | Yes | High | Foundation for all modules. | Module protocol
Channel | Output naming and icon association | Yes | Medium | Usability and identification. | Local DB
Input | Physical input modes: momentary, toggle, associated | Yes | Medium | Hardware behavior mapping. | Module protocol
Relay | Relay module control interface | Yes | High | Core supported device. | Channel control
Blind | DC blind motor control with UP/DOWN toggle logic | Yes | High | Supported device. | Module protocol
Dimmer | DC dimming module control (0-100%) | Yes | High | Supported device. | Module protocol
Dimmer | AC dimming module control (0-100%) | Yes | High | Supported device. | Module protocol
Temperature | Temperature monitoring and threshold alerts | Yes | High | Monitoring feature. | Module protocol
Scenario | Tap-to-run scenario creation and execution | Yes | High | Core automation value. | Scenario engine
Scenario | Multiple actions per scenario across modules | Yes | High | Complex scenarios. | Scenario engine
Scenario | Precise brightness levels in scenarios | Yes | High | Accurate dimming. | Dimmer control
Scenario | Manual dimmer slider scenario | Yes | Medium | Interactive adjustment. | Dimmer slider
Automation | Smart automations: time-of-day triggers | Yes | Medium | Time-based automation. | Scenario engine
Automation | Smart automations: device-state triggers | Yes | Medium | State-based automation. | Scenario engine
Events | Event history with 30-day retention | Yes | High | Audit and troubleshooting. | Event log
Rooms | Room/zone creation and scenario assignment | Yes | Medium | Organization. | Scenario engine
Home | Home screen quick scenario buttons | Yes | High | Fast access. | Scenario engine
Home | Drag-and-drop ordering of home scenario buttons | Yes | Medium | Customization. | Home buttons
Status | Offline module alert banner and System Status page | Yes | High | Monitoring and troubleshooting. | Status detection
Notifications | Push: module offline/online, long-running output, temperature threshold | Yes | Medium | Timely alerts. | FCM/APNs
Localization | Romanian and English localization at launch | Yes | High | Target market requirement. | i18n system
Multi-location | Single-location support (multi-location architecture ready) | Yes | Medium | Meets MVP scope; future-ready. | Data model
Thermostat | Advanced thermostat functionality (deferred to future level) | No | Low | Deferred; requires extended logic. | None
Cloud Portal | Cloud portal for remote equipment administration (deferred) | No | Low | Out of MVP scope; future release. | None